## Factory
Factory Fabrication Installation Cost Calculator - October 2020
By: Timothy D. Stark, Ph.D., P.E., D.GE, F.ASCE
Fabricated Geomembrane Institute
University of Illinios at Urbana-Champaign
Input Parameters
Calculated
Factory Fabrication Installation Cost Estimating - Large Panels
| Area | 1000000 | square feet, net lined area
| Deployment/shape factor | 1 | e.g., range 0.75 (all slope) to 1.25 (all flat)
| Panel Width | 125 | feet, e.g., for 40 mil reinforced FML
| Panel Length | 400 | feet, e.g., for 40 mil reinforced FML
| Number of Panels | 20 | e.g., for 40 mil reinforced FML
| Feet of Basic Seam | 8000 | feet, net lined area divided by panel width
| Feet of Cross Seam | 2500 | feet, basic seam length divided by panel length
| Total Seam length | 10500 | feet, total seam length (need to check panel layout)
| Length of Tie-in Seam | 1000 | feet, e.g., welded connection to exisiting liner
| Ave Seam Speed | 20 | feet/minute, assumed speed of primary seam wedge welder per minute
| Hours per Day | 8 | hours per work day on site
| Extra Hours per Day | 2 | extra hours per work day on site
| Set Up Time | 1 | i.e., basic no. days for factory production set up, ranging from 1 to 2 days depending on the length of the project
| Seaming Time | 2.3958 | i.e. basic no. days for factory production seaming assuming standard QC & 50% actual welding time
| Deployment Time | 0.625 | i.e., days to deploy & ballast geomembrane panels (assumes 0.25 hour per panel)
| Number of Details | 8 | pipe pentrations
| Time per Detail | 1 | hours
| Details Time | 1 | i.e., added days for detail work
| Total Days on Site | 4.0208 | i.e., assumes QC included |  |  |  | i.e. | 2489.6266 | sq-ft / man-hour
| Travel Time to Site | 0 | i.e., mobilization charge |  |  |  | i.e. | 5.7095 | acres per day
| Training Days Pre-Start | 0 | e.g., site specific safety training |  |  |  | i.e. | 4.0208 | days on site
| Days Total | 5.0208 | i.e., assumes QC included
| Non-Work Days | 2 | Sundays and rain/weather delays. Depending on duration of project and location, this ranges from 2-5
| Days Required |  | Unit Cost | Cost |  | Man-hours
| Supervisor | 1 | 60 | 2410 | non-union | 40.1667
| QC Tech | 1 | 50 | 2008.3333 | non-union | 40.1667
| Welding Techs | 2 | 40 | 3213.3333 | non-union | 80.3333
| Laborers | 4 | 20 | 3213.3333 | non-union | 160.6667
| Extra Hours |  | Unit Cost | Cost
| Supervisor | 1 | 90 | 903.75 | non-union | 10.0417
| QC Tech | 1 | 75 | 753.125 | non-union | 10.0417
| Welding Techs | 2 | 60 | 1205 | non-union | 20.0833
| Laborers | 4 | 30 | 1205 | non-union | 40.1667
|  |  |  | Cost |  | Cost
| Labor Total (Crew Size) | 8 |  | 10845 | non-union | 401.6667 | i.e. | 27 | ave. cost of labor per man hour
| Trucks | 3 | 30 | 3615 | i.e. charge out rate
| Generators | 2 | 20 | 1606.6667 | i.e. charge out rate
| Fuel | 0 | 20 | 0 | i.e. charge out rate
| Wedge Welders | 2 | 20 | 1606.6667 | i.e. charge out rate
| Other Tools & Equipment | 4 | 20 | 3213.3333 | i.e. charge out rate
| Large loader | 1 | 30 | 1205 | i.e. charge out rate
| Small loader | 1 | 20 | 803.3333 | i.e. charge out rate
| Equipment Total | 13 |  | 12050 | i.e. charge out rate |  | i.e. | 2400 | per day for equipment
| Hotel rooms | 5 | 120 | 3012.5
| Per diems | 8 | 40 | 1606.6667
| Mobilization | 8 | 750 | 6000
| Non-Work Day Expenses | 2 | 100 | 200
| Factory Project Total Cost |  |  | 33514.1667 |  |  | i.e. | 0.033514 | per sq. ft.
Does not include costs for materials.
Legal disclaimer regarding liability from cost and schedule related damages. This calculator is "For comparing cost purposes only" and a formal cost estimate should be conducted for each project

## Field
Field Fabrication Installation Cost Calculator - October 2020
By: Timothy D. Stark, Ph.D., P.E., D.GE, F.ASCE
Fabricated Geomembrane Institute
University of Illinios at Urbana-Champaign
Input Parameters
Calculated
Field Fabrication Installation Cost Estimating - Rolled Goods
| Area | 1000000 | square feet, net lined area
| Deployment/shape factor | 1 | e.g. range 0.75 (all slope) to 1.25 (all flat)
| Roll Width | 22.5 | feet, e.g. for 60 mil HDPE geomembrane
| Roll Length | 560 | feet, e.g. for 60 mil HDPE geomembrane
| Number of Rolls | 79.3651 | e.g. for 60 mil HDPE geomembrane
| Feet of Basic Seam | 44444.4444 | net lined area divided by roll width
| Feet of Cross Seam | 1785.7143 | basic seam length divided by roll length
| Total Seam length | 46230.1587 | feet, total seam length (need to check panel layout)
| Length of Tie-in Seam | 1000 | feet, e.g. welded connection to exisiting liner
| Ave Seam Speed | 22 | feet assumed speed of primary seam wedge welder per minute
| Hours per Day | 8 | hours per work day on site
| Extra Hours per Day | 2 | extra hours per work day on site
| Set Up Time | 2 | i.e. basic no. days for field production set up, ranging from 2 to 3 days depending on the length of the project
| Seaming Time | 8.9451 | i.e. basic no. days for field production seaming assuming standard QC & 50% actual welding time
| Deployment Time | 2.4802 | i.e. days to deploy & ballast geomembrane rolls (assumes 0.25 hour per roll)
| Number of Details | 8 | pipe pentrations
| Time per Detail | 1 | hours
| Details Time | 1 | i.e. added days for detail work
| Total Days on Site | 14.4253 | i.e. assumes QC included |  |  |  | i.e. | 866.5352 | sq-ft / man-hour
| Travel Time to Site | 0 | i.e. mobilization charge |  |  |  | i.e. | 1.5914 | acres per day
| Training Days Pre-Start | 0 | e.g. site specific safety training |  |  |  | i.e. | 14.4253 | days on site
| Days Total | 14.4253 | i.e. assumes QC included
| Non-Work Days | 3 | Sundays and rain/weather delays. Depending on duration of project and location, this ranges from 2-5
| Days Required |  | Unit Cost | Cost |  | Man-hours
| Supervisor | 1 | 60 | 6924.127 | non-union | 115.4021
| QC Tech | 1 | 50 | 5770.1058 | non-union | 115.4021
| Welding Techs | 2 | 40 | 9232.1693 | non-union | 230.8042
| Laborers | 4 | 20 | 9232.1693 | non-union | 461.6085
| Extra Hours |  | Unit Cost | Cost |  | Extra man-hours
| Supervisor | 1 | 90 | 2596.5476 | non-union | 28.8505
| QC Tech | 1 | 75 | 2163.7897 | non-union | 28.8505
| Welding Techs | 2 | 60 | 3462.0635 | non-union | 57.7011
| Laborers | 4 | 30 | 3462.0635 | non-union | 115.4021
|  |  |  | Cost |  | Cost
| Labor Total (Crew Size) | 8 |  | 42843.0357 | non-union | 1154.0212 | i.e. | 37.125 | av. cost of labor per man hour
| Trucks | 3 | 30 | 10386.1905 | i.e. charge out rate
| Generators | 2 | 20 | 4616.0847 | i.e. charge out rate
| Fuel | 0 | 20 | 0 | i.e. charge out rate
| Wedge Welders | 2 | 20 | 4616.0847 | i.e. charge out rate
| Other Tools & Equipment | 4 | 20 | 9232.1693 | i.e. charge out rate
| Large loader | 1 | 30 | 3462.0635 | i.e. charge out rate
| Small loader | 1 | 20 | 2308.0423 | i.e. charge out rate
| Equipment Total | 13 |  | 34620.6349 | i.e. charge out rate |  | i.e. | 2400 | per day for equipment
| Hotel rooms | 5 | 120 | 8655.1587
| Per diems | 8 | 40 | 4616.0847
| Mobilization | 8 | 750 | 6000
| Non-Work Day Expenses | 3 | 100 | 300
| Field Project Total Cost |  |  | 97034.914 |  |  | i.e. | 0.097035 | per sq. ft.
Does not include costs for materials.
Legal disclaimer regarding liability from cost and schedule related damages. This calculator is "For comparing cost purposes only" and a formal cost estimate should be conducted for each project

## Comparative Sheet
Fabrication cost comparison - October 2020
By: Timothy D. Stark, Ph.D., P.E., D.GE, F.ASCE
Fabricated Geomembrane Institute
University of Illinios at Urbana-Champaign
Cost comparison
|  |  | Field | Factory
Cost
|  | Labor Total (Crew Size) | 42843.0357 | 10845
|  | Equipment Total | 34620.6349 | 12050
|  | Hotel rooms | 8655.1587 | 3012.5
|  | Per diem | 4616.0847 | 1606.6667
|  | Mobilization | 6000 | 6000
|  | Non-Work Day Expenses | 300 | 200
|  | Project Total Cost | 97034.914 | 33514.1667
If choosing factory fabricated pannels for deployment, total savings will be:
63520.7474
Time comparison
|  |  | Field | Factory
Time (days)
|  | Days total | 14.4253 | 5.0208
|  | Non work days | 3 | 2
If choosing factory fabricated pannels for deployment, the time saved is:
|  |  |  | 10.4044 | days
Does not include costs for materials.
Legal disclaimer regarding liability from cost and schedule related damages. This calculator is "For comparing cost purposes only" and a formal cost estimate should be conducted for each project