## Factory
Factory Fabrication Installation Cost Calculator - April 2021
By: Timothy D. Stark, Ph.D., P.E., D.GE, F.ASCE
Fabricated Geomembrane Institute
University of Illinios at Urbana-Champaign
Input Parameters
Calculated
Factory Fabrication Installation Cost Estimating - Large Panels
| Area (squre feet) | 1000000 | square feet, net lined area
| Deployment/shape factor | 1 | e.g., range 0.75 (all slope) to 1.25 (all flat)
| Panel Width (feet) | 200 | feet, e.g., for 40 mil reinforced FML
| Panel Length (feet) | 400 | feet, e.g., for 40 mil reinforced FML
| Number of Panels | 12.5 | e.g., for 40 mil reinforced FML
| Feet of Basic Seam | 5000 | feet, net lined area divided by panel width
| Feet of Cross Seam | 2500 | feet, basic seam length divided by panel length
| Total Seam length | 7500 | feet, total seam length (need to check panel layout)
| Length of Tie-in Seam (feet) | 1000 | feet, e.g., welded connection to exisiting liner
| Ave Seam Speed (ft/minute) | 20 | feet/minute, assumed speed of primary seam wedge welder per minute
| Hours per Day | 6 | hours per work day on site
| Extra Hours per Day | 0 | extra hours per work day on site
| Set Up Time | 1 | i.e., basic no. days for factory production set up, ranging from 1 to 2 days depending on the length of the project
| Seaming Time | 2.3611 | i.e. basic no. days for factory production seaming assuming standard QC & 50% actual welding time
| Deployment Time | 0.52083 | i.e., days to deploy & ballast geomembrane panels (assumes 0.25 hour per panel)
| Number of Details | 8 | pipe pentrations
| Time per Detail | 1 | hours
| Details Time | 1.3333 | i.e., added days for detail work
| Total Days on Site | 5.2153 | i.e., assumes QC included |  |  |  | i.e. | 3994.6738 | sq-ft / man-hour
| Travel Time to Site | 0 | i.e., mobilization charge |  |  |  | i.e. | 4.4018 | acres per day
| Training Days Pre-Start | 0 | e.g., site specific safety training |  |  |  | i.e. | 5.2153 | days on site
| Days Total | 5.2153 | i.e., assumes QC included
| Non-Work Days | 2 | Sundays and rain/weather delays. Depending on duration of project and location, this ranges from 2-5
| Days Required |  | Unit Cost | Cost |  | Man-hours
| Supervisor | 1 | 60 | 1877.5 | non-union | 31.2917
| QC Tech | 1 | 50 | 1564.5833 | non-union | 31.2917
| Welding Techs | 2 | 40 | 2503.3333 | non-union | 62.5833
| Laborers | 4 | 20 | 2503.3333 | non-union | 125.1667
| Extra Hours |  | Unit Cost | Cost
| Supervisor | 1 | 90 | 0 | non-union | 0
| QC Tech | 1 | 75 | 0 | non-union | 0
| Welding Techs | 2 | 60 | 0 | non-union | 0
| Laborers | 4 | 30 | 0 | non-union | 0
|  |  |  | Cost |  | Man-hours
| Labor Total (Crew Size) | 8 |  | 8448.75 | non-union | 250.3333 | i.e. | 33.75 | ave. cost of labor per man hour
| Trucks | 3 | 30 | 2816.25 | i.e. charge out rate
| Generators | 2 | 20 | 1251.6667 | i.e. charge out rate
| Fuel | 0 | 20 | 0 | i.e. charge out rate
| Wedge Welders | 2 | 20 | 1251.6667 | i.e. charge out rate
| Other Tools & Equipment | 4 | 20 | 2503.3333 | i.e. charge out rate
| Large loader | 1 | 30 | 938.75 | i.e. charge out rate
| Small loader | 1 | 20 | 625.8333 | i.e. charge out rate
| Equipment Total | 13 |  | 9387.5 | i.e. charge out rate |  | i.e. | 1800 | per day for equipment
| Hotel rooms | 5 | 120 | 3129.1667
| Per diems | 8 | 40 | 1668.8889
| Mobilization | 8 | 750 | 6000
| Non-Work Day Expenses | 2 | 100 | 200
| Factory Project Total Cost |  |  | 28634.3056 |  |  | i.e. | 0.028634 | per sq. ft.
Does not include costs for materials.
Legal disclaimer regarding liability from cost and schedule related damages.
This calculator is "For comparing cost purposes only" and a formal cost estimate should be conducted for each project

## Field
Factory Fabrication Installation Cost Calculator - April 2021
By: Timothy D. Stark, Ph.D., P.E., D.GE, F.ASCE
Fabricated Geomembrane Institute
University of Illinios at Urbana-Champaign
Input Parameters
Calculated
Field Fabrication Installation Cost Estimating - Rolled Goods
| Area (squre feet) | 1000000 | square feet, net lined area
| Deployment/shape factor | 1 | e.g. range 0.75 (all slope) to 1.25 (all flat)
| Panel Width (feet) | 22.5 | feet, e.g. for 60 mil HDPE geomembrane
| Panel Length (feet) | 560 | feet, e.g. for 60 mil HDPE geomembrane
| Number of Rolls | 79.3651 | e.g. for 60 mil HDPE geomembrane
| Feet of Basic Seam | 44444.4444 | net lined area divided by roll width
| Feet of Cross Seam | 1785.7143 | basic seam length divided by roll length
| Total Seam length | 46230.1587 | feet, total seam length (need to check panel layout)
| Length of Tie-in Seam (feet) | 1000 | feet, e.g. welded connection to exisiting liner
| Ave Seam Speed (ft/minute) | 22 | feet assumed speed of primary seam wedge welder per minute
| Hours per Day | 6 | hours per work day on site
| Extra Hours per Day | 0 | extra hours per work day on site
| Set Up Time | 2 | i.e. basic no. days for field production set up, ranging from 2 to 3 days depending on the length of the project
| Seaming Time | 11.9268 | i.e. basic no. days for field production seaming assuming standard QC & 50% actual welding time
| Deployment Time | 3.3069 | i.e. days to deploy & ballast geomembrane rolls (assumes 0.25 hour per roll)
| Number of Details | 8 | pipe pentrations
| Time per Detail | 1 | hours
| Details Time | 1.3333 | i.e. added days for detail work
| Total Days on Site | 18.567 | i.e. assumes QC included |  |  |  | i.e. | 1122.0613 | sq-ft / man-hour
| Travel Time to Site | 0 | i.e. mobilization charge |  |  |  | i.e. | 1.2364 | acres per day
| Training Days Pre-Start | 0 | e.g. site specific safety training |  |  |  | i.e. | 18.567 | days on site
| Days Total | 18.567 | i.e. assumes QC included
| Non-Work Days | 3 | Sundays and rain/weather delays. Depending on duration of project and location, this ranges from 2-5
| Days Required |  | Unit Cost | Cost |  | Man-hours
| Supervisor | 1 | 60 | 6684.127 | non-union | 111.4021
| QC Tech | 1 | 50 | 5570.1058 | non-union | 111.4021
| Welding Techs | 2 | 40 | 8912.1693 | non-union | 222.8042
| Laborers | 4 | 20 | 8912.1693 | non-union | 445.6085
| Extra Hours |  | Unit Cost | Cost |  | Extra man-hours
| Supervisor | 1 | 90 | 0 | non-union | 0
| QC Tech | 1 | 75 | 0 | non-union | 0
| Welding Techs | 2 | 60 | 0 | non-union | 0
| Laborers | 4 | 30 | 0 | non-union | 0
|  |  |  | Cost |  | Cost
| Labor Total (Crew Size) | 8 |  | 30078.5714 | non-union | 891.2169 | i.e. | 33.75 | av. cost of labor per man hour
| Trucks | 3 | 30 | 10026.1905 | i.e. charge out rate
| Generators | 2 | 20 | 4456.0847 | i.e. charge out rate
| Fuel | 0 | 20 | 0 | i.e. charge out rate
| Wedge Welders | 2 | 20 | 4456.0847 | i.e. charge out rate
| Other Tools & Equipment | 4 | 20 | 8912.1693 | i.e. charge out rate
| Large loader | 1 | 30 | 3342.0635 | i.e. charge out rate
| Small loader | 1 | 20 | 2228.0423 | i.e. charge out rate
| Equipment Total | 13 |  | 33420.6349 | i.e. charge out rate |  | i.e. | 1800 | per day for equipment
| Hotel rooms | 5 | 120 | 11140.2116
| Per diems | 8 | 40 | 5941.4462
| Mobilization | 8 | 750 | 6000
| Non-Work Day Expenses | 3 | 100 | 300
| Field Project Total Cost |  |  | 86880.8642 |  |  | i.e. | 0.086881 | per sq. ft.
Does not include costs for materials.
Legal disclaimer regarding liability from cost and schedule related damages.
This calculator is "For comparing cost purposes only" and a formal cost estimate should be conducted for each project

## Comparative Sheet
Factory Fabrication Installation Cost Calculator - April 2021
By: Timothy D. Stark, Ph.D., P.E., D.GE, F.ASCE
Fabricated Geomembrane Institute
University of Illinios at Urbana-Champaign
Cost comparison
|  |  | Field | Factory
Cost
|  | Labor Total (Crew Size) | 30078.5714 | 8448.75
|  | Equipment Total | 33420.6349 | 9387.5
|  | Hotel rooms | 11140.2116 | 3129.1667
|  | Per diem | 5941.4462 | 1668.8889
|  | Mobilization | 6000 | 6000
|  | Non-Work Day Expenses | 300 | 200
|  | Project Total Cost | 86880.8642 | 28634.3056
If choosing factory fabricated pannels for deployment, total savings will be:
58246.5586
Time comparison
|  |  | Field | Factory
Time (days)
|  | Days total | 18.567 | 5.2153
|  | Non work days | 3 | 2
If choosing factory fabricated pannels for deployment, the time saved is:
|  |  |  | 14.3517 | days
Does not include costs for materials.
Legal disclaimer regarding liability from cost and schedule related damages. This calculator is "For comparing cost purposes only" and a formal cost estimate should be conducted for each project