## Sheet1
PHASE |  |  |  |  | DETAILS |  | TIMELINE
[7 empty] | Month before Event |  |  |  | Month of Event
| PROJECT WEEK: |  |  | Done? | Enter the date of the first Monday of each month --> |  | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4
| Onboarding |  |  |  | - Onboard Teams
- Set Expectations
- Q&A
| Project Definition and Planning |  |  |  | - Ticketing |  | Month before Event Week 1: Tickets
[5 empty] | - Registration/Reception |  | Month before Event Week 1: Registration; Month before Event Week 2: Reception
[5 empty] | - Sponsors |  | Month before Event Week 1: Sponsors
[5 empty] | - Stage Set Up (Virtual & Live) |  | Month before Event Week 2: Stage
[5 empty] | - Speakers |  | Month before Event Week 2: Speakers
[5 empty] | - Networking / Sessions |  | Month before Event Week 2: Sessions
[5 empty] | - Schedule |  | Month before Event Week 2: Schedule
[5 empty] | - Registrations / Eventbrite/ Marketo |  | Month before Event Week 2: Set up any 3rd party Marketing or Registration Integrations
[5 empty] | - Expo Booth Set Up |  | Month before Event Week 3: Expo
| Testing/Finessing |  |  |  | - Communication Plan |  | Month before Event Week 2: Communicate the event plan with all involved parties
[5 empty] | - Venue Controls |  | Month before Event Week 3: Event Dashboard > Venue > Venue Controls
[5 empty] | - Test Events |  | Month of Event Week 1: Tests
[5 empty] | - Speaker Dry Runs |  | Month of Event Week 1: Speaker - StreamYard Backstage Dry-Runs
| Event |  |  |  | - Pre-Event Check In |  | Month of Event Week 2: Pre-Event Check
[5 empty] | - Event |  | Month of Event Week 3: Event
[5 empty] | - Debrief |  | Month of Event Week 4: Event Reports
Ticketing: Remember when you are loading the tickets, they will go in on the page in the order you created them, depending on price point
Speakers: When keying them into the platform, remember they will load onto the page in the opposite order. The first one you put in, is the last one to show. If you want them in alphabetical order, you will need to load them that way, starting with the last speaker.
Sessions: Remember when setting Sessions, if you only want them to appear in certain times, you will need to tie them to the schedule as well.
Schedule: It may be easier to upload the schedule via CSV, but remember that the items will initially appear as they are in the CSV. Also, download the sample schedule CSV to make uploading easier!
Registration: Remember this will often be the first impression your attendees will have of your event. Make sure your description is concise yet inviting. You can include hyperlinks to your website, your T&C, or even reroute your attendees back to Eventbrite to register. You can change font color by accessing the font button, or if you would prefer a color that is not included in that selection, create your description in Google Docs, use any font color there and then copy and paste back to the Description box.
CSS: Change colors in the platform using CSS |  | (on Advanced Plans only) | Introduction to Advanced Branding |  | Dark Theme | Highlighted Theme
Expo: You can let your Sponsors set up their own Expo Booths.
Stage: The listing of the Stages will appear in the same order as they are created. Keep this in mind when creating stages. The default stage can be renamed, but will remain at the top.
Test Events: You will want to create test events for your speaker dry runs by duplicating your event. You will want to put it closer to the event so your Speakers will remain confident in what they've learned on the day of the event.